## Priority list
Dam Safety Program - Project Priority Needs List | [5 empty] | DNR Ecological and Water Resources
Prepared as directed by Minnesota Statutes Section 103G.511, Subdivision 12 | [8 empty] | Updated May 20, 2011
(Dollars in Thousands)
Priority | Name | Owner | County | DNR | Hazard | Project Type | Est | State's | Cumulative | Primary Needs | Owner | Local | Comments
Ranking |  |  |  | Region | Class |  | Cost | Cost | State Cost |  | Contacted | Support
funded | Shell Rock (Albert Lea Lake) | County | Freeborn | 4 | 2-Med. | Replace | 500 | 250 |  | maintain lake levels |  |  | Issue - ownership issue close to resolution
funded | Rush Creek | DNR | Chisago | 3 | N/A | Remove/restore | 200 | 200 |  | restore fish passage |  |  | Removal in 2011
funded | New London | DNR | Kandiyohi | 4 | 1-High | Rehabilitate | 2950 | 2950 |  | safety/maintain lake levels |  |  | Project wrap up in 2011
funded | Jackson | City | Jackson | 4 | 2-Med. | Remove/modify | 1000 | 150 |  | safety/restore fish passage |  |  | Construction underway
funded | Windom | City | Cottonwood | 4 | N/A | Remove/restore | 300 | 150 |  | safety/restore fish passage |  |  | Issue - remove or restore the dam
funded | Cross Lake | DNR | Pine | 2 | 3-Low | Modify | 225 | 225 |  | safety/restore fish passage |  |  | Currently in design phase
funded | Hartley (Duluth) | City | St. Louis | 2 | 1-High | Modify | 500 | 250 |  | safety/maintain lake levels |  |  | Scope of project being defined; dam break
funded | Luverne | City | Rock | 4 | 3-Low | Remove/modify | 150 | 75 |  | safety/restore fish passage |  |  | Project complete
funded | Christine | City | Wilkin | 1 | 3-Low | Modify | 400 | 25 |  | safety/restore fish passage |  |  | Project in 2011
funded | Hickson | City | Clay | 1 | 3-Low | Modify | 400 | 25 |  | safety/restore fish passage |  |  | Project in 2011
funded | Lake Bronson | DNR | Kittson | 1 | 1-High | Rehab. eng. | 800 | 800 |  | safety/maintain lake levels | DNR | Yes | Final design work; $9M reconstruction est.
funded | Pike River | DNR | St. Louis | 2 | 2-Med. | Modify eng. | 225 | 225 |  | safety/maintain lake levels | DNR | Maybe | poor condition
funded | Clayton Lake | DNR | Pine | 2 | 3-Low | Repair | 325 | 325 |  | safety/historic preservation | DNR | Yes | historic, project is ready, SHPO approval
funded | Montevideo | City | Chippewa | 4 | 2-Med. | Remove | 300 | 150 |  | safety/restore fish passage | Yes | Yes | community support for removal, damaged
funded | Lanesboro | City | Fillmore | 3 | 1-High | Repair/rehab | 900 | 450 |  | safety/historical preservation | Yes | Yes | Issue - City funding
funded | Drayton | Drayton, ND | Kittson | 1 | 2-Med. | Remove/modify | 1000 | 250 |  | safety/restore fish passage | Yes | Yes | many drownings, issues; $ for MN side only
funded | Champlin Mill Pond | City | Hennepin | 3 | 2-Med. | Repair/modify | 500 | 250 |  | safety | Yes | Yes | WSB study, ownership, water qualitiy
funded | Milaca | City | Mille Lacs | 3 | 3-Low | Remove | 300 | 150 |  | safety/restore fish passage | Yes | No | drowning machine, City decision on removal
funded | Hallock | City | Kittson | 1 | 3-Low | Remove/modify | 300 | 150 |  | safety/restore fish passage | Yes | Maybe | need better PR, golf course, communicate
funded | Madison Lake | ? | Blue Earth | 4 | 3-Low | Replace | 100 | 50 |  | maintain lake levels |  |  | Orphan dam, project in 2011
funded | Shady Lake | County | Olmsted | 3 | 2-Med. | Remove | 1000 | 1000 |  | safety |  | Yes | 2010 special session bonding
funded | Byllesby | County | Dakota/Goodhue | 3 | 1-High | Repair | 4800 | 850 |  | safety | Yes | Yes | PMF increase in capacity via FERC
1 | Byllesby | County | Dakota/Goodhue | 3 | 1-High | Repair | 4800 | 1550 | 1550 | safety | Yes | Yes | This would bring DNR contribution to 50%
2 | Lake Bronson | DNR | Kittson | 1 | 1-High | Rehab. eng. | 9000 | 9000 | 10550 | safety/maintain lake levels | DNR | Yes | Final design work; $9M reconstruction est.
3 | Coon Rapids | County | Hennepin | 3 | 2-Med. | Repair/modify | 16000 | 16000 | 26550 | safety |  |  | Fish passage barrier
4 | Balsam Lake | DNR | Itasca | 2 | 3-Low | Repair | 250 | 250 | 26800 | safety/maintain lake levels | DNR | Yes | Local support; concrete deterioration
5 | Lizzie | DNR | Otter Tail | 1 | 3-Low | Modify | 25 | 25 | 26825 | maintain lake levels | DNR |  | Don - Bog - maintainance headache
6 | Perkins Lake | DNR | Stevens | 3 | 3-Low | Repair | 200 | 200 | 27025 | safety/maintain lake levels | DNR | Maybe | Don-put in steel and redo; remove crossing
7 | Brawner | DNR | Lyon | 4 | 3-Low | Repair/remove | 250 | 250 | 27275 | safety | DNR | Maybe | Dan-misc in bad shape, Parks and trail
8 | Pelican Lake | DNR | Otter Tail | 1 | 3-Low | Repair | 200 | 200 | 27475 | maintain lake levels | DNR | Yes | Abutment - Local support is high
9 | Sullivan Lake | DNR | Morrison | 3 | 3-Low | Replace | 100 | 100 | 27575 | maintain lake levels | DNR | Yes | Abutment- Local support, earth work
10 | Height of Land Lake | DNR | Becker | 1 | 3-Low | Modify | 100 | 100 | 27675 | maintain lake levels | DNR |  | Don-Bog - cut low piers and repairs
11 | Coon Lake | DNR | Anoka | 3 | 3-Low | Repair | 100 | 100 | 27775 | maintain lake levels |  |  | Conduits need replacement; Anoka Co help
12 | Sand Hill Lake | DNR | Polk | 1 | 3-Low | Repair | 100 | 100 | 27875 | fish passage/maintain lake | DNR |  | Bezek-fish passage, frost heave
13 | Stalker | DNR | Otter Tail | 1 | 3-Low | Repair | 25 | 25 | 27900 | maintain lake levels | DNR |  | Don-put in steel, add fill to abutment
14 | Sauk River | City | Stearns | 3 | 3-Low | Remove | 150 | 75 | 27975 | safety |  |  | Dan Lais request, contact St Cloud
15 | Millerville | County | Douglas | 1 | 3-Low | Reconstruct | 100 | 50 | 28025 | safety |  |  | County road project
16 | Sweeney Lake | City | Hennepin | 3 | 3-Low | Replace | 200 | 100 | 28125 | maintain lake levels |  |  | Len Kramer-Barr; Golden Valley/Bassett Cr
17 | Titlow Lake | City | Sibley | 4 | 3-Low | Replace | 300 | 150 | 28275 | maintain lake levels |  |  | Rock dam falling apart
18 | Martin Lake | DNR | Anoka | 3 | 3-Low | Repair | 50 | 50 | 28325 | safety |  |  | Fisheries support; fish barrier; TMDL
19 | Shields | DNR | Rice | 4 | 3-Low | Repair | 100 | 100 | 28425 | maintain lake levels | DNR |  | Don-right abutment has failed
20 | State Hospital Pond | State | Nicollet | 4 | 2-Med. | Remove/modify | 500 | 500 | 28925 | safety |  |  | buildings may get wet, prefer removal
21 | Dam Lake | DNR | Aitkin | 2 | 3-Low | Repair | 100 | 100 | 29025 | maintain lake levels | DNR |  | Lonnie-both abutments
22 | Ten Mile | DNR | Otter Tail | 1 | 3-Low | Repair | 100 | 100 | 29125 | maintain lake levels | DNR |  | Don-redo dam and embankment, sill
23 | Deer Creek at Effie | DNR | Itasca | 2 | 3-Low | Replace | 250 | 250 | 29375 | safety/aesthetics | DNR |  | Don-Left abutment
24 | Eagle Lake | DNR | Crow Wing | 2 | 3-Low | Repair | 25 | 25 | 29400 | maintain lake levels | DNR |  | Don-put in steel, tampering
25 | Hanging Kettle Lake | DNR | Aitkin | 2 | 3-Low | Repair | 100 | 100 | 29500 | maintain lake levels | DNR |  | Don/Lonnie- both abutments falling
26 | Long (Tamefish) | DNR | Crow Wing | 2 | 3-Low | Repair/Modify | 50 | 50 | 29550 | maintain lake levels | DNR |  | sheep pile heave, rocks and debris
27 | Ripple Lake | DNR | Aitkin | 2 | 3-Low | Repair | 100 | 100 | 29650 | maintain lake levels | DNR |  | Don-put in steel, left abutment failing
28 | Wynne | DNR | St. Louis | 2 | 3-Low | Modify | 100 | 100 | 29750 | safety | DNR |  | Don-6 bays open, log jam, difficult access
29 | Rum River (Anoka) | City | Anoka | 3 | 3-Low | Modify | 600 | 300 | 30050 | safety |  | Yes | Ekman-inquiry; flashboard, big gate
30 | Homer township/Pickwick | Township | Winona | 3 | 2-Med. | Repair/modify | 300 | 150 | 30200 | safety/maintain lake levels |  |  | order to repair, verify hazard
31 | Sunrise River Pool #1 | DNR | Chisago | 3 | 3-Low | Modify | 75 | 75 | 30275 | safety | DNR |  | might act as a drowning machine
32 | Sunrise River Pool #2 | DNR | Chisago | 3 | 3-Low | Modify | 75 | 75 | 30350 | safety | DNR |  | might act as a drowning machine
33 | Clearwater River | Counties | Stearns/Wright | 3 | 3-Low | Repair | 300 | 150 | 30500 | safety |  |  | recent bike trail
34 | Big Stone Lake | WD/DNR | Big Stone | 4 | 2-Med. | Modify | 50 | 50 | 30550 | safety |  |  | Corps acceptance needed
35 | Woolen Mill (Faribault) | City | Rice | 4 | 2-Med. | Remove/modify | 400 | 200 | 30750 | safety |  |  | need scope of project
36 | Knife Lake | LID | Kanabec | 3 | 2-Med. | Modify | 500 | 250 | 31000 | safety |  |  | drowning machine?,Joe Raiolo,$ seems high
37 | Sunrise River (Kost) | County | Chisago | 3 | 3-Low | Modify | 100 | 50 | 31050 | safety | Yes | Not yet | Fishing hole; need further discussions
38 | Pine Lake | DNR | Aitkin | 2 | 3-Low | Repair | 150 | 150 | 31200 | maintain lake levels | DNR |  | Lonnie-not high priority, but keep on list
39 | George Lake | DNR | Anoka | 3 | 3-Low | Repair | 50 | 50 | 31250 | maintain lake levels | DNR |  | Don-should install heavy sheetpile
40 | Northern Light Lake | DNR/USFS | Cook | 2 | 3-Low | Repair | 50 | 50 | 31300 | maintain lake levels | DNR |  | need internal discussions
41 | Melrose | City | Stearns | 3 | 2-Med. | Modify | 400 | 200 | 31500 | safety |  |  | Lais-shoreland stabilization
42 | Pelican Rapids | City | Otter Tail | 1 | 1-High | Repair | 400 | 200 | 31700 | safety |  |  | Rock masonry wall leaning
43 | French Lake | County | Rice | 4 | 3-Low | Replace | 200 | 100 | 31800 | maintain lake levels |  |  | Joe McGough-5 years
44 | Fountain Lake (Albert Lea) | City | Freeborn | 4 | 3-Low | Modify | 300 | 150 | 31950 | safety |  |  | fish barrier?
45 | Abandoned mining dams | State | Various | 2 |  | Repair/remove | 500 | 500 | 32450 | safety |  |  | contact Jim Sellner, research
46 | Round | DNR | Becker | 1 | 3-Low | Modify | 25 | 25 | 32475 | fish passage/maintain lake | DNR | Yes | Fish/bridge project; funded with LSOHC
47 | Fish Lake | DNR | Kanabec | 3 | 3-Low | Modify | 250 | 250 | 32725 | safety/restore fish passage | DNR | Yes | Fisheries support; funded with LSOHC
48 | Sylvia | DNR | Stearns | 3 | 3-Low | Repair | 50 | 50 | 32775 | fish passage/maintain lake | DNR |  | Removal/riffle abutment repair; LSOHC
The remaining projects are grouped by DNR Region and are not prioritized.
| Shell Lake | DNR | Becker | 1 | 3-Low | Repair | 75 | 75 | 32850 | maintain lake levels |  |  | Don-put in steel, concrete deterioration
| Hattie Lake | DNR | Cass | 1 | 3-Low | Repair | 25 | 25 | 32875 | maintain lake levels |  |  | Don-put in steel, dam ok
| Miltona Lake | DNR | Douglas | 1 | 3-Low | Repair | 150 | 150 | 33025 | maintain lake levels |  |  | concrete deterioration, leaning left abutment
| Upper Hunt Lake | DNR | Douglas | 1 | 3-Low | Repair | 100 | 100 | 33125 | maintain lake levels
| Park Rapids (Fish Hook) | City | Hubbard | 1 | 2-Med. | Repair | 300 | 150 | 33275 | safety
| Portage Lake | DNR | Hubbard | 1 | 3-Low | Repair | 200 | 200 | 33475 | maintain lake levels
| Stephen | City | Marshall | 1 | 3-Low | Modify | 200 | 100 | 33575 | safety/restore fish passage
| Blanche | DNR | Otter Tail | 1 | 3-Low | Repair | 100 | 100 | 33675 | maintain lake levels |  |  | Don-put in steel, concrete pier deterioration
| Fergus Falls | City | Otter Tail | 1 | N/A | Remove remnants | 100 | 100 | 33775 | safety
| Little Pine Lake | DNR | Otter Tail | 1 | 3-Low | Repair | 100 | 100 | 33875 | maintain lake levels |  |  | Don-put top row in steel
| Long (Dalton) | DNR | Otter Tail | 1 | 3-Low | Repair | 50 | 50 | 33925 | maintain lake levels |  |  | Don-put in steel, concrete deterioration
| Long (Elizabeth) | DNR | Otter Tail | 1 | 3-Low | Repair | 50 | 50 | 33975 | maintain lake levels |  |  | Don-put in steel, concrete deterioration
| Prairie Lake | DNR | Otter Tail | 1 | 3-Low | Repair | 100 | 100 | 34075 | maintain lake levels |  |  | Don-repair right abutment, snowmobile trail
| Rose Lake | DNR | Otter Tail | 1 | 3-Low | Repair | 100 | 100 | 34175 | maintain lake levels
| Crissy Lake | DNR | Stevens | 1 | 2-Med. | Modify | 300 | 300 | 34475 | safety/restore fish passage
| Hill Lake | DNR | Aitkin | 2 | 3-Low | Repair | 50 | 50 | 34525 | maintain lake levels |  |  | Don-put in steel
| Greer Lake | DNR | Crow Wing | 2 | 3-Low | Repair | 100 | 100 | 34625 | maintain lake levels
| O'Brien Lake | DNR | Crow Wing | 2 | 3-Low | Repair | 100 | 100 | 34725 | maintain lake levels |  |  | steel recently installed
| Round Lake | DNR | Crow Wing | 2 | 3-Low | Repair | 25 | 25 | 34750 | maintain lake levels |  |  | Don-put in steel, concrete deterioration
| Upper South Long Lake | DNR | Crow Wing | 2 | 3-Low | Repair | 25 | 25 | 34775 | maintain lake levels |  |  | Don-put in steel, dam ok
| Buck Lake | DNR | Itasca | 2 | 3-Low | Modify | 100 | 100 | 34875 | safety/aesthetics
| Splithand Lake | DNR | Itasca | 2 | 3-Low | Remove | 100 | 100 | 34975 | safety/aesthetics
| Grindstone River (Hinckley) | DNR | Pine | 2 | 2-Med. | Replace/modify | 500 | 500 | 35475 | safety
| Willow River | DNR | Pine | 2 | 2-Med. | Modify | 300 | 300 | 35775 | safety
| Bear Lake | DNR | St. Louis | 2 | 3-Low | Replace | 100 | 100 | 35875 | maintain lake levels
| Esquagama Lake | DNR | St. Louis | 2 | 3-Low | Repair/modify | 500 | 500 | 36375 | maintain lake levels |  |  | Don-?
| Floodwood | DNR | St. Louis | 2 | 3-Low | Repair | 100 | 100 | 36475 | safety/maintain lake levels |  |  | Don-dam ok?
| Pequaywan | DNR | St. Louis | 2 | 3-Low | Repair | 50 | 50 | 36525 | safety/maintain lake levels |  |  | Don-fix eroded hole on apron
| Sturgeon Lake | DNR | St. Louis | 2 | 3-Low | Repair | 100 | 100 | 36625 | maintain lake levels |  |  | Don-?
| Bucksnort | private | Fillmore | 3 | 3-Low | Remove | 200 | 200 | 36825 | safety
| Mayowood (Rochester) | City | Olmsted | 3 | 3-Low | Modify | 500 | 250 | 37075 | safety
| Silver Lake (Rochester) | City | Olmsted | 3 | 2-Med. | Modify | 600 | 300 | 37375 | safety
| Cold Spring | DNR | Stearns | 3 | 3-Low | Modify | 500 | 500 | 37875 | safety
| Eden Lake | DNR | Stearns | 3 | 3-Low | Repair | 150 | 150 | 38025 | maintain lake levels |  |  | Don-put in stoplogs
| Sauk Centre | City | Stearns | 3 | 2-Med. | Modify | 500 | 250 | 38275 | safety
| Fairhaven | County | Wright/Stearns | 3 | 3-Low | Modify | 600 | 300 | 38575 | safety
| Rapidan | County | Blue Earth | 4 | 2-Med. | Remove | 15000 | 7500 | 46075 | safety/river restoration |  |  | energy dissipator Corps standards
| Springfield | not known | Brown | 4 | 3-Low | Remove/modfy | 300 | 150 | 46225 | safety/restore fish passage
| Talcot Lake | DNR | Cottonwood | 4 | 3-Low | Repair | 150 | 150 | 46375 | safety/maintain lake levels
| Warren Lake | DNR | Cottonwood | 4 | 3-Low | Repair | 250 | 250 | 46625 | safety/maintain lake levels
| Mantorville | City | Dodge | 4 | 3-Low | Repair/Modify | 300 | 150 | 46775 | safety/maintain lake levels
| Freeborn Lake | DNR | Freeborn | 4 | 3-Low | Repair | 100 | 100 | 46875 | maintain lake levels
| Washington Lake | not known | LeSueur | 4 | 3-Low | Repair | 100 | 100 | 46975 | maintain lake levels
| 4th Street (Austin) | private | Mower | 4 | 3-Low | Remove | 250 | 250 | 47225 | safety
| Louise Lake | DNR | Mower | 4 | 3-Low | Repair | 300 | 300 | 47525 | safety/restore fish passage
| Ramsey (Austin) | private | Mower | 4 | 3-Low | Remove/modify | 250 | 250 | 47775 | safety
| Ocheda | DNR | Nobles | 4 | 3-Low | Repair | 25 | 25 | 47800 | maintain lake levels |  |  | Don-put in steel, tampering
| Lamberton | County | Redwood | 4 | 3-Low | Remove/modify | 300 | 150 | 47950 | safety/restore fish passage
| Sanborn | not known | Redwood | 4 | 3-Low | Remove/modfy | 300 | 150 | 48100 | safety/restore fish passage
| Blue Mounds (Lower) | DNR | Rock | 4 | 3-Low | Repair | 300 | 300 | 48400 | maintain lake levels/historic pres.
| Clear Lake | County | Sibley | 4 | 3-Low | Replace |  |  | 48400 | maintain lake levels |  |  | leaning sheet pile, drawdown capability
| Curran Lake | County | Sibley | 4 | 3-Low | Repair | 100 | 50 | 48450 | maintain lake levels
| High Island | DNR | Sibley | 4 | 3-Low | Remove | 200 | 200 | 48650 | safety/restore fish passage
| Elysian Lake | DNR | Waseca | 4 | 3-Low | Repair | 150 | 150 | 48800 | maintain lake levels
| Granite Falls | City | Yellow Medicine | 4 | 1-High | Modify | 600 | 300 | 49100 | safety
Notes:
1) Priorities are subject to change based on results of dam safety inspections, readiness of local project sponsors, opportunities for piggybacking projects, etc.
2) All cost estimates are preliminary; actual costs will depend on final project design and construction bids received.
3) MS Section 103G.511 authorizes matching grants to local governments and requires legislative approval of projects or grants of $250,000 or more.
4) MS Section 103G.515 authorizes the state to pay the full cost of dam removals under certain conditions.
5) "Remove/modify" means a final decision has not been made on whether the dam will be removed or modified.
For more information contact: Steve Hirsch at (651) 259-5106, Kent Lokkesmoe at (651) 259-5701 , Dale Homuth at (651) 259-5133, or Jason Boyle at (651) 259-5715.

## Statute considerations
103G.511 PUBLICLY OWNED DAM REPAIR.
Subd. 6. Determination of grant. The commissioner shall consider all relevant factors in
determining whether to repair or reconstruct a state-owned dam or to make a grant to a political
subdivision including:
(1) the age and type of construction of the dam;
(2) the use of the dam for water supply, flood control, navigation, hydroelectric power
generation, recreation, wildlife management, scenic value, or other purposes related to public
health, safety, and welfare;
(3) the consequences of abandonment, removal, or alteration of the dam;
(4) prospective future uses of the dam; and
(5) the relative importance of the dam to the statewide water resource program.
Subd. 12. Priority list of dams needing repair. After reviewing examinations of dams
owned by the state and political subdivisions, the commissioner shall prioritize the state and
political subdivision dams in need of repair, reconstruction, or removal and report by June 1 of
each odd-numbered year to the legislature. The commissioner must prioritize projects considering
danger to life, damage to property, and the factors listed in subdivision 6.