## Timeline_SAMPLE
Project Timeline Natural and Scenic Area MN Grant Application [Agency customize and insert Grant Name Here]
Applicant name: | [Applicant Name]
Project: | [Project Name]
County: | [County Name]
Planned duration
ACTIVITY | Start Month | Activity Duration (months) | MONTH
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Grant Agreement Finalized | 1 | 1 | bar: MONTH 1
Updated Appraisal received/sent to review committee | 2 | 1 | bar: MONTH 1
Baseline report - stakeholder review | 2 | 2 | bar: MONTH 2 to MONTH 3
Stewardship management plan finalized | 3 | 2 | bar: MONTH 3 to MONTH 4
Purchase agreement finalized | 5 | 2 | bar: MONTH 5 to MONTH 6
Closing documents signed | 7 | 1 | bar: MONTH 7
Final Land survey | 7 | 1 | bar: MONTH 7
Title Work and Purchase agreement | 7 | 1 | bar: MONTH 7
Final Proof od Filed deed restriction | 8 | 1 | bar: MONTH 8
Final on-site inspection | 8 | 1 | bar: MONTH 8
Final 10% reimbursement | 9 | 1 | bar: MONTH 9
Final Grant Closeout Letter | 10 | 2 | bar: MONTH 10
Record retention (6 years) | 10 | 72 | bar: MONTH 10 to MONTH 24

## Timeline_TEMPLATE
Project Timeline Natural and Scenic Area MN Grant Application [Agency customize and insert Grant Name Here]
Applicant name: | [Applicant Name]
Project: | [Project Name]
County: | [County Name]
Planned duration
ACTIVITY | Start Month | Activity Duration (months) | MONTH
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24