## Timeline_SAMPLE
Project Timeline Outdoor Recreation MN Grant Application [Agency customize and insert Grant Name Here]
Applicant name: | [Applicant Name]
Project: | [Project Name]
County: | [County Name]
Planned duration
ACTIVITY | Start Month | Activity Duration (months) | MONTH
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
OR Agreement Finalized | 1 | 1 | bar: MONTH 1
Final Design Phase | 2 | 3 | bar: MONTH 2 to MONTH 4
Public Bid Process | 5 | 2 | bar: MONTH 5 to MONTH 6
Contract Awarded | 7 | 1 | bar: MONTH 7
Project Construction | 8 | 15 | bar: MONTH 8 to MONTH 22
Progress Report | 12, 24 | 1 | bar: MONTH 12; MONTH 24
Reimbursement Requests | 13 | 1 | bar: MONTH 13; MONTH 22 to MONTH 23
Construction closeout | 22 | 2 | bar: MONTH 24
Reimbursement Requests | 24 | 1 | bar: MONTH 25
Final Onsite Inspection | 26 | 1 | bar: MONTH 26
Final 10% reimbursement | 27 | 1 | bar: MONTH 27
Final Grant Closeout | 27 | 2 | bar: MONTH 27 to MONTH 28
Record retention (6 years) | 27 | 9 | bar: MONTH 27 to MONTH 36

## Timeline_TEMPLATE
Project Timeline Outdoor Recreation MN Grant Application [Agency customize and insert Grant Name Here]
Applicant name: | [Applicant Name]
Project: | [Project Name]
County: | [County Name]
Planned duration
ACTIVITY | Start Month | Activity Duration (months) | MONTH
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36